## Meeting Agenda
Date | 08.06.2025
1 | Review of the task
2 | Alignment on Terms and Conditions
Date | 29.06.2025
1 | Review of the task
2 | Open email address
3 | Update task sheet
4 | Improvement in communication

## Task
Task | Responsible | Priority | Due Date | Status
Develop a web prototype for the app | Victor | High | 29.06.2025 | Done
Buy domain - Research | Victor | High | 05.07.2025 | Done
Buy Domain - Purchase | Somoye | High | 06.07.2025 | Done
Open email | Victor | High | 29.06.2025 | Done
Open Github | Victor | High | 06.07.2025 | Done
Open domain email | Somoye | High | 06.07.2025 | Done
Upload html to Github | Victor | High | 13.07.2025 | Done
Upload python to Github | Somoye | High | 13.07.2025 | Done
Prepare and integration of Python and Html | Victor | High | 13.07.2025 | Done
Prepare and integration of Python and Html | Somoye | High | 05.10.2025 | In progress
New Front end design (sprint 1) | Victor | High | 05.10.2025 | In progress
Integration of backend | Somoye | High | 05.10.2026 | In progress
Research competitors | Victor | High | 05.10.2028 | Done

## User stories
| Main deliverable | Acceptance criteria | Responsible | Deadline
1 | Generate notebook summary | Users should be able to view a summary of their uploaded notebooks after upload is completed | Somoye | 21.09.2025
2 | Ask a question from the notebook | After the summary is displayed, users should be able o question thier notebooks | Somoye | 05.10.2025
3 | Generate Questions | Users should be able to generate questions | Somoye | 05.10.2025

## Passwords
Web | Username | Password
Mail | info@studyassists.com
| info.studyassists.gmail.com | SomoyeVictor29062025

## Backlog
App Improvement | Priorities
Scenario based questions
Reason why it is the correct answer e.g Page number
Being able to integrate into an API
Testing of the result accuracy
Ability to have Pictures displayed as Question
Mathematics integration
Decide on either using flask or Django
Progress bar
User interaction
Inclusion of the ability to select between teachers and students
Inclusion of the ability to download results
Inclusion of the ability to download questions
Potential Use Cases
WAEC
JAMB
NECO
Private School - Internal Use
Marketing
Sales and Marketing - Yakub
Gift card based subscription